## Dashboard
Farmhouse Construction ERP | Farmhouse Construction ERP | Farmhouse Construction ERP | Farmhouse Construction ERP | Farmhouse Construction ERP | Farmhouse Construction ERP | Farmhouse Construction ERP | Farmhouse Construction ERP
Total Project Budget | 5810000 |  | Category | Budget | Actual | Remaining
Total Spent | 290000 |  | Material | 2340000 | 213000 | 2127000
Remaining Budget | 5520000 |  | Machinery | 270000 | 32000 | 238000
Budget Utilization | 4.991% |  | Labour | 850000 | 45000 | 805000
No. of Vendors | 5 |  | Electrical | 300000 | 0 | 300000
No. of Transactions | 4 |  | Plumbing | 250000 | 0 | 250000
Current Stage | Foundation |  | Solar | 500000 | 0 | 500000
Last Updated | 2026-06-29 |  | Security | 120000 | 0 | 120000
|  |  | Civil | 580000 | 0 | 580000
|  |  | Professional | 300000 | 0 | 300000
|  |  | Government | 100000 | 0 | 100000

## Import Statements
Date | Account | Narration | Withdrawal | Deposit | Reference | Balance

## Master Ledger
Date | Account | Type | Amount | Vendor | Narration | Category | Subcategory | Stage | Payment Mode | Invoice No | Remarks
2026-06-01 | Bank | Expense | 125000 | ABC Steel Traders | TMT steel advance | Material | Steel | Foundation | Bank Transfer | INV-001
2026-06-03 | Cash | Expense | 32000 | Ravi JCB Services | Excavation equipment | Machinery | JCB | Excavation | Cash | INV-002
2026-06-07 | Bank | Expense | 88000 | Sri Cement Depot | Cement bags | Material | Cement | Foundation | UPI | INV-003
2026-06-10 | Cash | Expense | 45000 | Mason Team | Mason labour weekly | Labour | Mason | Foundation | Cash | WAGE-001

## Vendor Master
Vendor | Aliases | Default Category | Default Subcategory | Phone/UPI | Notes
ABC Steel Traders | ABC Steel;Steel Traders | Material | Steel
Sri Cement Depot | Cement Depot;Sri Cement | Material | Cement
Ravi JCB Services | Ravi JCB;JCB | Machinery | JCB
Mason Team | Mason;Masonry | Labour | Mason
Electrical Works | Electrician;Electrical | Electrical | Electrical

## Categories
Category | Subcategory | Budget
Material | Steel | 800000
Material | Cement | 450000
Material | M-Sand | 300000
Material | P-Sand | 250000
Material | Jelly | 220000
Material | Bricks | 320000
Machinery | JCB | 150000
Machinery | Tractor | 120000
Labour | Mason | 500000
Labour | Helper | 350000
Electrical | Electrical | 300000
Plumbing | Plumbing | 250000
Solar | Solar | 500000
Security | CCTV | 120000
Civil | Borewell | 180000
Civil | Compound Wall | 400000
Professional | Architect | 150000
Professional | Engineer | 150000
Government | Approvals | 100000
Other | Misc | 200000

## Material Register
Date | Material | Quantity | Unit | Vendor | Rate | Amount | Remarks
2026-06-01 | Steel | 2.5 | Ton | ABC Steel Traders | 50000 | 125000 | Foundation steel
2026-06-07 | Cement | 200 | Bag | Sri Cement Depot | 440 | 88000 | Foundation cement

## Budget vs Actual
Category | Budget | Actual | Remaining | % Used
Material | 2340000 | 213000 | 2127000 | 9.103%
Machinery | 270000 | 32000 | 238000 | 11.85%
Labour | 850000 | 45000 | 805000 | 5.294%
Electrical | 300000 | 0 | 300000 | 0%
Plumbing | 250000 | 0 | 250000 | 0%
Solar | 500000 | 0 | 500000 | 0%
Security | 120000 | 0 | 120000 | 0%
Civil | 580000 | 0 | 580000 | 0%
Professional | 300000 | 0 | 300000 | 0%
Government | 100000 | 0 | 100000 | 0%

## Project Stages
Stage | Budget | Spent | % Complete | Notes
Site Clearing | 150000 | 0 | 0%
Excavation | 250000 | 32000 | 12.8%
Foundation | 900000 | 258000 | 28.67%
Columns | 600000 | 0 | 0%
Roof | 650000 | 0 | 0%
Masonry | 450000 | 0 | 0%
Electrical | 300000 | 0 | 0%
Plumbing | 250000 | 0 | 0%
Solar | 500000 | 0 | 0%
CCTV | 120000 | 0 | 0%
Finishing | 700000 | 0 | 0%
Landscaping | 250000 | 0 | 0%

## Documents
Date | Vendor | Invoice No | Document Name | File Path | Remarks

## README
How to use this workbook
1. Paste bank statement rows into Import Statements.
2. Add or clean transaction rows in Master Ledger. Yellow cells are editable inputs.
3. Keep Categories budgets updated; Budget vs Actual and Dashboard recalculate from these values.
4. Add vendors once in Vendor Master and reuse the names in ledger/document tracking.
5. Track material quantities in Material Register; Amount is calculated as Quantity x Rate.
6. Keep invoices and file locations in Documents so payments remain auditable.
7. Project Stages shows spend by construction phase using the Stage column in Master Ledger.
8. Do not type over blue calculated cells unless you intentionally want to replace formulas.
9. Extend rows by copying the formatting/formulas from the rows above.